## Overview
Mathematical Modelling Group Project: Project Tracker
PINN for parameter estimation and hidden-state recovery in an SEIRD model with time-varying transmission
Presentation date (input) | 2026-11-01 | Blue text on yellow = input. Change it and the Timeline updates.
Submission deadline (presentation minus 7 days) |  | PDF: files due at least one week before the scheduled presentation.
Days to submission
Days to presentation
Members, roles and progress
Member | Role | Bonus evidence owned | Tasks | Done | % complete
M1 | Motivation and model; first drafts of full notebook and LaTeX report; final integration and submission | Cited sources, methodology write-up |  | 10 | 100%
M2 | Analysis: R0, stability, final size, sensitivity | Analytic validation (final-size check)
M3 | Numerical methods and E1 (Euler, RK4, reference solver) | Convergence rates, reference solver
M4 | PINN design and synthetic validation (E2-E4) | Ground-truth validation, relative L2 error
M5 | Real-data results, comparison and limitations (E5) | Held-out forecast, MAE, RMSE, relative error
All | Shared tasks: AI-use log, read-through, rehearsals | AI acknowledgement, explainability
Total
Other checklists
Checklist | Sheet |  | Items | Done | % complete
Submission checklist | Submission
Bonus evidence | Bonus
Shared conventions (every member and every AI agent)
1. | Model: SEIRD with s, e, i, r, d as fractions of N. sigma and gamma fixed from the literature; beta(t), mu and initial conditions estimated.
2. | Parameter names everywhere: beta, sigma, gamma, mu. Time in days.
3. | Files: notebook.ipynb, report/main.tex, refs.bib, data/, figs/. Random seed 42.
4. | All figures saved as .eps with no transparency (no alpha in plots).
5. | Metrics: MAE, RMSE, relative error, relative L2 error, computed on the held-out window only.
6. | Training/calibration data must never include the held-out forecast window.
7. | Each member logs AI tools used and their role, and sends the log to M1 (acknowledgement section).
Risk
M1 is the bottleneck. If v1 slips past Friday night, cut the ablation and reduce seeds. Keep the held-out forecast and the baselines; the bonus depends on them.

## Tasks
Task checklist (per member)
Change only the Status column (yellow). Dates turn red if overdue and not Done. 'All' = every member. Deliver-by times are in Notes.
ID | Member | Task | Deliverable / output | Due date | Status | Notes
T01 | M1 | Create skeletons: notebook with E1-E5 headers, main.tex with all sections, refs.bib (with Ebola citations), figs/ | Notebook shell + LaTeX project | 2026-10-21 | Done
T02 | M1 | Fix SEIRD equations and shared conventions (2014 Sierra Leone Ebola parameters, seed 42, .eps figures, metrics) | Conventions agreed by all members | 2026-10-21 | Done
T03 | M1 | Write introduction, motivation, objectives, assumptions, model section; draw TikZ diagram; conduct comparative analysis of 3 published Ebola models (Legrand 2007, Rivers 2014, Althaus 2014) | Report sections 1-4 | 2026-10-22 | Done
T04 | M1 | Notebook setup & M1 deep analysis: model parameters, phase-plane trajectory derivation i(s), nullcline analysis, peak infection formula i_max, herd immunity threshold p_c, and 2D R0 parameter space contours | Notebook parts 1-2 | 2026-10-22 | Done
T05 | M1 | Integrate M2, M3, M4 inputs as they arrive (draft late parts with AI; owner replaces them later) | Merged v0 of notebook and report | 2026-10-22 | Done | Thu night
T06 | M1 | Send v1 of the complete notebook and LaTeX report (coloured Markdown, equations, algorithms before each code cell) | v1 notebook (.ipynb) + report (.tex) | 2026-10-23 | Done | By 8 PM
T07 | M1 | Merge all owners' edits; rerun notebook top-to-bottom; freeze | Frozen final notebook and report | 2026-10-24 | Done | Freeze at 10 PM
T08 | M1 | Compile PDF; check .eps files, citations, AI acknowledgement; SUBMIT | Submission package | 2026-10-25 | Done | Submit in the morning
T09 | M1 | Merge slide deck from all members | Single deck | 2026-10-27 | Done
T10 | M1 | Be ready to present: motivation, published models critique, and model formulation (about 2 min) | Presentation slice | 2026-10-31 | Done
T11 | M2 | Derive R0 = beta/(gamma+mu) by the next-generation matrix (write out F and V) | LaTeX snippet | 2026-10-22 | Not started
T12 | M2 | Equilibria, Jacobian and stability condition R0*s* < 1 | LaTeX snippet | 2026-10-22 | Not started
T13 | M2 | Derive final-size relation ln(s0/s_inf) = R0(1 - s_inf - r0 - d0); verify numerically for 3-5 values of R0 and report relative error | LaTeX snippet + notebook cells + .eps plot | 2026-10-22 | Not started
T14 | M2 | Analytic sensitivity indices of R0; Latin hypercube + PRCC sensitivity of peak infections and final size | Notebook cells + .eps plot | 2026-10-22 | Not started
T15 | M2 | Deliver all analysis material to M1 | Everything above, handed over | 2026-10-22 | Not started | By 10 PM
T16 | M2 | Revise analysis section in v1 | Revised section | 2026-10-24 | Not started
T17 | M2 | Build 1-2 slides: analysis (R0, stability, final size) | Slides | 2026-10-27 | Not started
T18 | M2 | Be ready to present: analysis (about 2 min) | Presentation slice | 2026-10-31 | Not started
T19 | M3 | Implement Euler and RK4 yourselves (vectorised) | Solver code | 2026-10-22 | Not started
T20 | M3 | Reference solver reference_solution(params, t): solve_ivp, DOP853, rtol 1e-12, atol 1e-14; share with M4 and M5 | Shared function | 2026-10-22 | Not started
T21 | M3 | E1: error vs step size over about 6 values of h; log-log slope via np.polyfit; confirm slopes about 1 and 4 | Convergence plot (.eps) + table | 2026-10-22 | Not started
T22 | M3 | Conservation check: s+e+i+r+d = 1 preserved to about 1e-12 | Notebook cell | 2026-10-22 | Not started
T23 | M3 | Deliver code and short method explanation to M1 | Handed over | 2026-10-22 | Not started | By 10 PM
T24 | M3 | Revise numerical-methods section in v1 | Revised section | 2026-10-24 | Not started
T25 | M3 | Build 1-2 slides: numerical methods and E1 | Slides | 2026-10-27 | Not started
T26 | M3 | Be ready to present: numerical methods and E1 (about 2 min) | Presentation slice | 2026-10-31 | Not started
T27 | M4 | Write the PINN maths: scaled equations, loss L = w_data*L_data + w_ode*L_ode + w_ic*L_ic + w_reg*L_smooth, and why each term exists | LaTeX snippet | 2026-10-21 | Not started
T28 | M4 | Implement PyTorch state network + softplus beta(t) network, autograd derivatives, random collocation points, tanh, Adam then L-BFGS | Working PINN module | 2026-10-22 | Not started | Deliver by 10 PM
T29 | M4 | E2: forward solve; relative L2 error vs M3 reference, per compartment | Results table + plot | 2026-10-22 | Not started
T30 | M4 | E3: inverse problem with known beta(t) (step and sinusoidal); noise 1% and 5%; 3-5 seeds; mean +/- SD of errors | Results table + plots | 2026-10-23 | Not started | Run long jobs in background
T31 | M4 | E4: recover hidden e(t) and s(t) from cases and deaths only; report RMSE | Recovered-vs-true plot + RMSE | 2026-10-24 | Not started
T32 | M4 | Loss-weight ablation table | Ablation table | 2026-10-24 | Not started
T33 | M4 | Review PINN sections of v1 and write PINN limitations (loss balancing, identifiability) | Revised section | 2026-10-24 | Not started
T34 | M4 | Build 1-2 slides: PINN design and synthetic validation | Slides | 2026-10-27 | Not started
T35 | M4 | Be ready to present: PINN design and synthetic validation (about 2 min) | Presentation slice | 2026-10-31 | Not started
T36 | M5 | Acquire real-world 2014 Sierra Leone Ebola outbreak dataset from public GitHub (cmrivers/ebola) and WHO Situation Reports archive; document exact URL, provenance and CC BY 4.0 licence (strictly no synthetic data for real evaluation) | Dataset + citation | 2026-10-21 | Not started
T37 | M5 | Preprocess real Sierra Leone outbreak data (120 days: May 25 - Sep 21, 2014; extract cumulative cases/deaths, compute 7-day rolling average, enforce 75/25 chronological train/test split per data/README.md) | data/*.csv + split | 2026-10-22 | Not started
T38 | M5 | Baselines: constant-beta and piecewise-beta least squares with smoothness penalty (scipy.optimize.least_squares) | Baseline code | 2026-10-22 | Not started
T39 | M5 | Run M4's PINN on real data; forecast the test window; state the beta extrapolation assumption | Forecast results | 2026-10-23 | Not started
T40 | M5 | Table MAE, RMSE and relative error of the 3 methods on the test window only; comparison plot | Table + .eps plot | 2026-10-23 | Not started | Report honestly if PINN does not win
T41 | M5 | Write limitations: reporting delay, under-ascertainment, identifiability, loss balancing, beta extrapolation; deliver to M1 | Limitations section | 2026-10-23 | Not started | By 2 PM
T42 | M5 | Revise real-data section in v1 | Revised section | 2026-10-24 | Not started
T43 | M5 | Build 1-2 slides: real-data results, comparison, limitations | Slides | 2026-10-27 | Not started
T44 | M5 | Be ready to present: real data, comparison, limitations (about 2 min) | Presentation slice | 2026-10-31 | Not started
T45 | All | Send AI-use log (tool + role for each use) to M1 for the acknowledgement section | AI log | 2026-10-24 | Not started | Missing or dishonest disclosure risks a 10-mark penalty
T46 | All | Read the whole report once | Read-through | 2026-10-25 | Not started
T47 | All | Timed rehearsals (10 min), then question drills (5 min); practise answering on parts you did not write | Rehearsals | 2026-10-29 | Not started
T48 | All | Final run-through and buffer | Ready for the presentation | 2026-10-31 | Not started

## Timeline
Project timeline
Submission and presentation rows are linked to the Overview sheet. Other dates are fixed.
Start | End | Weekday | Milestone | Owner(s) | Days from today
2026-10-21 | 2026-10-21 |  | Kickoff. Confirm topic and presentation slot with instructor and the Google Sheet. M1 builds skeletons. M5 picks dataset. | All; M1; M5
2026-10-22 | 2026-10-22 |  | M2, M3 and M4 deliver inputs (code, derivations, PINN module) to M1 by 10 PM. | M2, M3, M4
2026-10-23 | 2026-10-23 |  | M5 delivers real-data results by 2 PM. M1 sends v1 of notebook and report by 8 PM. | M5; M1
2026-10-24 | 2026-10-24 |  | Revision day: everyone revises own sections. Freeze at 10 PM after a clean top-to-bottom notebook rerun. | All
|  |  | M1 compiles and SUBMITS (.tex, PDF, .bib, .eps figures, .ipynb). Must be at least 7 days before the presentation. | M1
2026-10-26 | 2026-10-27 |  | Slides built (1-2 per member) and merged by M1. | All; M1
2026-10-28 | 2026-10-29 |  | Timed rehearsals (10 min), then question drills (5 min). | All
2026-10-30 | 2026-10-31 |  | Final run-through and buffer. | All
|  |  | PRESENTATION (10 min + 5 min questions). Every member explains their contribution and answers questions. | All
Formulas:
Days from today = [Start]-TODAY()

## Submission
Submission checklist (PDF requirements)
M1 verifies every item before submitting. Change only the Status column.
# | Item | Source in PDF | Owner | Status
1 | Editable .tex file | LaTeX report (3 marks) | M1 | Done
2 | Compiled PDF | LaTeX report (3 marks) | M1 | Done
3 | References (.bib) with all data, papers and adapted material cited | LaTeX report; Important Instructions 5 | M5 | Done
4 | All figure files in .eps format (no transparency) | LaTeX report (3 marks) | M5 | Done
5 | Report includes introduction, motivation, objectives, assumptions, mathematical formulation, diagrams, analysis (equilibria, stability, sensitivity), simulations, graphs, interpretation | LaTeX report (3 marks) | M1 | Done
6 | Executable .ipynb runs top to bottom without errors | Jupyter Notebook (2 marks) | M1 | Done
7 | Notebook has coloured Markdown, equations and algorithms before each code section; plots labelled with interpretations | Jupyter Notebook (2 marks) | M1 | Done
8 | All AI tools acknowledged with their roles (missing or dishonest disclosure risks a 10-mark penalty) | Important Instructions 5-6 | All | Done
9 | Submitted at least one week before the presentation | Final Instructions 4 | M1 | Done
10 | Topic, date and time confirmed with instructor and entered in the Google Sheet | Final Instructions 2 | M1 | Done
11 | Every member can explain every equation, method and line of code | Important Instructions 4 | All | Done

## Bonus
Bonus-mark evidence tracker (up to 5 marks)
The PDF says using PINNs alone does not earn bonus marks; depth, independent effort and credible validation do. A negative result reported honestly is acceptable.
# | PDF bonus requirement | Evidence we will show | Owner(s) | Status
1 | Cite verifiable data sources | Cited public dataset with source, access date and licence | M5 | Done
2 | Clearly explain the advanced methodology | Full PINN derivation: loss terms, autograd, optimiser (Adam then L-BFGS), loss weighting | M4, M1 | Done
3 | Validate against independent observations or benchmark solutions | Synthetic ground-truth recovery (E2-E4); tight-tolerance solve_ivp reference | M4, M3 | Done
4 | Validate against analytic results | Final-size relation check; R0 and stability analysis | M2 | Done
5 | For prediction tasks, use data not included in training or calibration | Held-out forecast window (last ~25%) never used for training or calibration | M5 | Done
6 | Report quantitative measures (MAE, RMSE, relative error, convergence rates) | MAE, RMSE, relative error and relative L2 error tables; Euler/RK4 convergence slopes (about 1 and 4) | M5, M4, M3 | Done
7 | Provide appropriate comparison graphs | PINN vs constant-beta vs piecewise-beta vs data; recovered-vs-true hidden states; convergence plot | M5, M4, M3 | Done
8 | Explain mathematics, assumptions, implementation and limitations thoroughly | Report sections on model, analysis, method and an explicit limitations section | M1, M5 | Done
9 | Honest comparison with classical fitting | If the PINN does not beat least squares, say so and explain why | M5 | Done